## Tasks
Station | WBS | Task (improved name) | Planned min | Steps | Σ step min | Σ = planned? | Description (proposed) | Safety notes (proposed) | Verify: invented? | Verify: dropped? | Review flags / issues
Disassembly | 1 | Fluid Drain and Labeling | 15 | 3 | 15 | yes | Drain the unit's fluids into a collection bucket. While the fluid drains, label the generator panels so they can be identified later for reinstall. First prep task in the Current State Disassembly lane — performed before any panels or modules are removed. | • Never remove the radiator cap on a hot or pressurized system — allow the unit to cool first. Hot coolant can spray and cause burns. • Wear nitrile gloves and safety glasses — coolant and other fluids are toxic and irritate skin/eyes. • Contain all drained fluid and clean spills immediately to prevent slip hazards. • Store and dispose of drained fluids per facility hazardous-waste procedures. | no | no | • ✓ APPLIED TO DATABASE (task version 220) • Already reviewed and applied.
Disassembly | 2 | Panel Removal | 35 | 3 | 35 | yes | Remove the exterior panels from the donor diesel genset during teardown, using sockets and impact guns to free their fasteners. Panels and their hardware are sorted onto carts by use and stored so they can be reused or reworked in later sub-assembly and final-assembly stages. | • Panels are unfastened with impact guns and sockets; the loosened panel can shift or drop once its bolts are removed, creating a pinch and crush hazard for hands and feet. • Sheet-metal panels have sharp edges and corners; handle and lift them carefully to avoid laceration injuries when removing and loading onto carts. • Impact guns and powered sockets present rotating-tool and flying-debris hazards; keep hands clear of the socket and wear eye protection while driving fasteners. • Removed panels staged and stacked on carts can become unstable; place them in their intended sequence and secure them so they do not tip or fall during handling. | YES ⚠ | no | • single source step split into 3 logical groupings (Remove -> Store hardware -> Sort onto carts) • source note 'In future we will have them labeled' reflected as 'panels are not yet labeled', no invented labeling action • no torque/spec values present in source; none added • kept full socket/impact-gun tool set verbatim from source • INVENTED ACTION (step 1): instruction adds 'so identify them by location' — the source only states 'Remove panels - In future we will have them labeled'. The source never instructs the operator to identify panels by location; this is a fabricated physical action, not a grounded paraphrase of the 'not yet labeled' note. • FALSE change_note (step 1): change_note is 'verbatim' but the instruction is NOT verbatim. Source: 'Remove panels - In future we will have them labeled'. Rewrite: 'Remove the panels using the sockets and impact guns (panels are not yet labeled, so identify them by location).' It both reworded the labeling note and injected the new 'identify by location' action, so labeling it 'verbatim' is inaccurate. • MINOR added rationale (step 2): 'correct hardware storage is critical for reassembly' appends '...for reassembly', which is not in the source. Source bullet 3 only says 'Its critical to place hard ware in correct storage areas'. The 'critical' framing is grounded; the 'for reassembly' purpose is a mild inference not stated in the source notes.
Disassembly | 3 | Remove Control Cabinet | 30 | 3 | 30 | yes | Disconnect and remove the diesel genset's control cabinet during teardown, freeing it and its associated wiring from the donor unit so the chassis can be prepped for the hybrid retrofit. This involves detaching all electrical connections (alternator, harness, sensors, grounds, starter solenoid) and then removing the cabinet's base mounting bolts. | • The control cabinet harness, alternator wires, and starter solenoid wire may carry stored electrical energy; confirm the unit is de-energized and battery is disconnected before detaching any conductors to avoid shock or short-circuit. • Fuel level and containment level sensors tie into the fuel system; disconnect carefully and be alert for residual fuel exposure or spillage at the sensor ports. • Removing the base cabinet bolts can release the cabinet's weight or pinch hands; support the cabinet and keep fingers clear as the final fasteners come out. • Detaching the wire harness bar and ground wire can leave loose conductors; label or secure free ends to prevent trip hazards and accidental contact. | no | no | • 1 source step expanded into 3 logical groupings • reordered: bolt removal moved to last so all electrical connections are detached before the cabinet is freed mechanically • no tools listed on source task or step - none invented • 16 photos present on source step but not represented in structured steps
Disassembly | 4 | Remove Cooling and After-Treatment Components | 30 | 4 | 30 | yes | Strip the diesel genset's cooling and DEF after-treatment hardware off the donor unit so the engine/alternator module can be removed downstream. This covers intercooler flanges, fan shroud, fuel valve system, the engine-block DEF cooling lines, the engine-to-fuel-tank ground, and the DEF tank (which the team plans to retain on the unit). | • DEF cooling lines and the DEF tank may still hold Diesel Exhaust Fluid - have a catch tray ready and wear eye/skin protection to avoid spill and contact with the fluid. • The fuel valve system can retain residual diesel and pressure - relieve/cap lines and contain drips to prevent a flammable spill. • Disconnect the engine-block-to-fuel-tank ground strap to break stored-energy/electrical paths before working around fuel and metal components. • Cooling and after-treatment surfaces may be hot if the genset ran recently - confirm components are cool before removing intercooler flanges, fan shroud, and DEF lines. • The DEF tank is being kept on the unit - support and secure it during line removal so it does not shift or drop and crush a hand. | no | no | • single source step split into 4 logical groupings • kept DEF line markers 03022 (front) / 03018 (back) verbatim • reordered: fuel-valve/ground disconnects moved ahead of cooling/DEF mechanical removal for logical sequence • only tool on source is a 10mm wrench; no other tools invented • DEF tank to be retained on unit per source note
Disassembly | 5 | Remove Engine / Alternator Module | 20 | 3 | 20 | yes | Tear down and free the diesel genset's engine/alternator module from the donor chassis so it can be lifted out and transferred to the jig during hybrid retrofit. This removes the residual fluid drains, retaining hardware, fan shroud, and mounting bolts, then rigs and lifts the engine while leaving the rigging attached for the jig hand-off. | • Engine/alternator module is a heavy load: rig, lift, and transfer to the jig with the crane only when clear of personnel to avoid crush injuries. • Oil and fuel drains/lines are being opened or freed: capture residual oil and fuel to prevent flammable spills and slip hazards. • Remove the grounding wire and verify the module is electrically isolated before working to avoid shorts or stored-energy hazards. • Mount and housing bolts may be under load: support the module before backing out the top alternator mount bolts to control stored tension and pinch points. • Leave the rigging attached to the engine during transfer; do not stand under or reach beneath the suspended load. | no | no | • 1 source step expanded into 3 logical groupings (disconnect/de-mount/lift) • reordered raw notes for logical sequence; no actions/tools/values added • kept 'leave oil filter housing' and 'leave rigging in engine' instructions verbatim • source note 'Currently we are transferring engine to the jig' treated as context for the lift step, not invented as a separate action
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 73 | 6 | 73 | yes | Removes the donor genset's fuel tank and reworks its fuel hose, then transfers the engine and alternator mounts to the new chassis and refits the chassis onto the new fuel tank in preparation for hybrid build-up. This frees the chassis from the original containment tank and stages the lower assembly for downstream final assembly on the trailer. | • Fuel tank and fuel hose handling: lift the tank to keep fuel from leaking and route the new fuel line carefully - flammable fuel and spill hazard; keep ignition sources away and contain any drips. • Lifting the chassis out of the containment tank and dropping it back onto the new fuel tank uses a crane for positioning - heavy-load crush/swing hazard; keep hands and body clear of the load path while it is suspended. • Loosening the motor mount screws while the mount is loaded releases stored load - keep fingers clear and expect the mount to shift as tension is released. • Removing perimeter fuel-tank bolts and perimeter/top strap nuts can free components under load - pinch and stored-tension hazard as straps and the tank are released. • Routing the new fuel line risks pinching the hose during chassis reassembly - confirm the line is clear of pinch points before dropping the chassis. | no | no | • Split dense 18-bullet source step 2 (63 min) into 4 logical groupings: transfer mounts, free/lift tank, rework hose/reinstall, refit chassis; distributed its 63 min across them (13/18/16/16) • Steps 1 and 6 kept verbatim from source • Kept '11 ft of 3/8\" fuel hose' and 'rotate barb 180 degrees' values verbatim • Source step 2 quality_check was 'Loctite' - not carried into instructions as no application action was specified in the notes • Single planned operator: all steps sequential (concurrent=false) • Minor (description, not a step instruction): the description's phrase 'stages the lower assembly for downstream final assembly on the trailer' introduces 'the trailer', which appears nowhere in the source. Source project context only mentions 'one-piece-flow donor teardown and hybrid prep' with no trailer. Not invented data per the strict instruction-only rule, but the trailer is an ungrounded specific physical artifact in the authored description.
Sub Assemblies | 7 | Battery Build | 0 | 3 | 0 | yes | Builds the upgraded battery pack sub-assembly off-line for the FlexBoost hybrid retrofit, so the completed module is ready for installation at Final Assembly. The source step contained no operator notes, so this breakdown is authored from the task name and project context only and must be reviewed and filled in with the actual build procedure, fasteners, and specs. | • Battery packs carry stored electrical energy: verify the pack is de-energized/isolated and avoid shorting terminals with metal tools before and during the build. • The battery module is heavy: use proper lifting technique or a crane/jig and keep hands clear of pinch points when positioning it to avoid crush injury. • Fastening with the 1 1/8" socket on an impact gun or ratchet can create pinch/strike hazards: keep fingers clear of the socket and rotating tool. • Source notes are empty - actual hazards are unknown; do not begin the build until the real procedure, voltages, and fastener specs are confirmed. | YES ⚠ | no | • NO SOURCE DATA - fully authored, needs review • Source step is empty (no instruction text, no step name) - only data is task name 'Battery Build' and one tool • planned_duration_minutes is 0 - all step durations set to 0 • 0 operators on source task • kept only tool '1 1/8" socket' verbatim; no part numbers, torque specs, or extra tools invented • SAFETY NOTE assumes electrical hazard with no source basis (source step instruction is empty, no voltage/energy data): 'Battery packs carry stored electrical energy: verify the pack is de-energized/isolated and avoid shorting terminals with metal tools before and during the build.' • SAFETY NOTE assumes the module is heavy AND invents lifting equipment (crane/jig) not in source tools (only tool is '1 1/8" socket'): 'The battery module is heavy: use proper lifting technique or a crane/jig and keep hands clear of pinch points when positioning it to avoid crush injury.' • SAFETY NOTE + step instructions INVENT a driver tool ('impact gun or ratchet') not present in source; source lists only '1 1/8" socket': 'Fastening with the 1 1/8" socket on an impact gun or ratchet can create pinch/strike hazards...' • INVENTED ACTION/PART in step 2 instruction: source has no instruction text and only the tool '1 1/8" socket'; the rewrite asserts fasteners and a tighten action: 'Install and tighten the fasteners using the 1 1/8" socket.' (a socket implies fastening, but 'fasteners' as a part and the join action are authored, not sourced) • INVENTED ACTION in step 2 instruction with no source basis (empty source step): 'Position and join the battery pack components into the upgraded module.'
Sub Assemblies | 8 | Panel rework station | 172 | 7 | 172 | yes | Rework the genset's exterior panels and doors into upgraded hybrid-spec parts at the Sub Assemblies offline station: transfer accessories (hinges, handles, baffle boxes, plates, bump stops) from the old panels onto updated panels, then install the specified foam seals, baffle foam, and perimeter gaskets. This prepares the seven panels (3, 4, 5, 6, 9, 10, 11) so they are ready for the hybrid unit's final assembly with proper acoustic/thermal sealing. | • Drilling out baffle/screw holes and through rivets (step bit, may drill through rivets) creates sharp swarf and flying chips - wear eye protection and clear debris before handling. • Removing and reinstalling hinges, handles, and baffle boxes uses the 3/8" impact gun and sockets - keep fingers clear of pinch points between panel, hinge, and bench, and beware sudden release of fasteners. • Sheet-metal panels, doors, and cover plates have sharp cut edges and rivet holes - handle panel transfers and louver/cover-plate installs with cut-resistant gloves. • Using a scraper to remove foam from baffle-box edges can slip - cut away from the body and keep the free hand clear of the blade path. • Panel 6 radiator cover plate is left open for filling and Panel 5 is part of the cooling stack - verify orientation and leave the fill access clear to avoid trapping/spilling coolant downstream. | no | no | • 0 operators on source task (planned_operators=0) • Kept all foam/part numbers verbatim: 1466/1467 (Panel 4), 1646/1469/1470/1468 (Panel 10), 1457/1458/1459 (Panels 11 & 9), 1645 (Panel 9), 1456/1477 (Panel 3), 1463/1475/1476 (Panel 6), 1460/1461/1462/1464/1465/1473/1474/1472/1471 (Panel 5) • Kept source's 7-step (one-per-panel) structure; only fixed grammar/spelling and added imperative titles • Step durations already summed to planned 172 min; preserved as-is • Stripped trailing tab/whitespace artifacts from source step titles • No quality_check values present in source
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 140 | 6 | 140 | yes | Build the upgraded V2 cooling sub-assembly off-line for the FlexBoost hybrid retrofit: fit foam panels and seals to cooling unit part 1300, mount the fans, reservoir, radiator, cooling tower and inverter onto panels 3 and 5, then complete the coolant plumbing (drain system and hoses) before moving the finished assembly to panel 5. This module is later joined to the hybrid unit during Final Assembly. | • Widening/reaming radiator and part 1300 holes with a step bit and chasing threads throws metal chips and creates hot, sharp burrs - wear eye protection and gloves and deburr edges. • The completed cooling assembly with radiator, fans and reservoir is heavy and is moved between panel 3 and panel 5 - keep hands clear of pinch points and get help or a lift for the transfer. • The inverter component sits proud on its bracket and bolts are left loose for the air inlet/radiator body - watch for the assembly shifting or bolts backing out while handling. • Punching holes through foam seal and handling worm/hose clamps and threaded fasteners presents pinch and laceration hazards - keep fingers clear of the punch and clamp jaws. | no | no | • 0 operators on source task (planned_operators=0) • Source step durations were 5 + 135 = 140; step 2 (135 min) split into 5 logical sub-assembly groups, durations distributed proportionally to sum to planned 140 • Kept all part numbers verbatim (1300, 1478/1479/1480, 27, 31, 35, 19, 33, 32, 21, 22, 20, 16, 17, 28, 24, 23, 25, 26, 13, 18, 15, 30, part 3, part 5) and fastener specs (M6 x 30, M6 x 15mm, M6 x 30mm, 7/16” washer, 3/4” hex socket) • Source step 2 named an incomplete trailing action 'install f' which was omitted as it had no actionable content • task_tools (10mm Socket, 3/8” angled electric ratchet) attached only to source step 2; not duplicated as invented tools on prep/plumbing steps
Sub Assemblies | 10 | mVEC / DC-DC Converter Build | 40 | 2 | 40 | yes | Assembles the upgraded power-electronics sub-module for the FlexBoost hybrid retrofit by mounting the mVEC relay box and the DC-DC converter to their brackets and wiring them together. This off-line build prepares a complete mVEC/DC2DC module ready for installation during Final Assembly. | • Mounting the mVEC relay box and DC-DC converter to brackets involves power-electronics units - confirm they are de-energized and any stored charge is discharged before handling. • When adding the wiring harness, verify the assembly is electrically isolated to avoid shorting connectors or exposing live conductors. • Secure each component fully to its bracket before releasing it to prevent the unit from dropping or pinching hands during mounting. | no | no | • 0 operators on source task • source task_tools and step tools are empty - no tools added • two source steps kept as-is; only grammar/titles added
Sub Assemblies | 11 | Upgrade Control Cabinet | 153 | 6 | 153 | yes | Build out the upgraded hybrid control cabinet as an off-line sub-assembly: mount the DIN rail and controller hardware, install the 480V contactor and CAN-bus junction, then wire the Tinkerer, mVEC, and DC2DC harnesses. The final step moves to final assembly to install the FlexBoost main harness that ties the cabinet to the cooling system, inverter, e-motor, clutch, and pumps for the converted hybrid power unit. | • 480V contactor and the 480V/12V signal wiring carry high voltage and stored energy - verify the cabinet is de-energized and follow lockout before terminating or connecting these circuits. • CAN-bus, mVEC, and DC2DC 12V harness connections involve live low-voltage control circuits and connector pins - mismate or shorts can damage power electronics, so confirm pin assignments before energizing. • Self-tappers and DIN rail mounting create sharp edges and burrs inside the cabinet - watch for cuts and metal swarf near the wiring. • Main-harness ground must be bonded to the engine ground correctly; an improper ground bond is an electrical-fault and shock hazard once the hybrid unit is powered. • Routing harnesses to the front of the cabinet and onto the cooling system involves reaching into a populated enclosure - mind pinch points between connectors and panel edges. | no | no | • 0 operators on source task (planned_operators=0) • no tools listed on source task or any step - none invented • kept hardware names verbatim: Tinkerer, mVEC harness 1604, DC2DC, 480V contactor, CAN 1 port, resistor A-B, pin 3 • step 4 source duration is only 1 min for a 6-action harness install - likely a data-entry error, but kept verbatim to preserve 153-min sum • step 6 carries a source caveat ('Possibly install on cooling system first') and moves to final assembly - preserved as written
Sub Assemblies | 12 | Build E-Motor Assembly | 45 | 3 | 45 | yes | Prepares the upgraded e-motor module off-line in the Sub Assemblies station by installing its coolant fittings so the motor is ready for V2 cooling hookup during final hybrid assembly. The source notes cover only the coolant fitting installation: the elbow fitting goes in first, followed by the straight fitting. | • Threading and torquing coolant fittings with a ratchet and crescent wrench can pinch or skin knuckles if a tool slips - keep a firm grip and clear your hand path. • Seat each fitting (elbow then straight) without cross-threading or over-tightening; a stripped or over-torqued port can crack the housing and cause a coolant leak at the cooling-circuit interface later. • The e-motor module is a heavy sub-assembly - secure and chock it on the bench before applying wrench force so it cannot shift or roll. | YES ⚠ | no | • 0 operators on source task • Source task title says 'Build E Motor Assembly' but the only source step covers installing motor coolant fittings - no other assembly actions present; did not invent any • Step 1 (staging) is change_note=ADDED - reasonable prep grounded in the listed tools/fittings, needs review • Steps 2-3 kept verbatim: elbow fitting first, then straight fitting • step_count=1 on source; split into 3 logical steps per granularity convention • INVENTED ACTION (step 1 instruction): 'Secure the e-motor module on the bench and gather the elbow and straight coolant fittings.' — securing/positioning the module on a bench is a physical handling action with no basis in the source. The source's only step covers 'Install motor coolant fittings / Elbow fitting installed first. / Then install Straight fitting'; it contains zero handling, positioning, or securing actions. (The tool layout — '26mm socket, 1/2" ratchet, crescent wrench, and 1" socket' — and 'gather ... coolant fittings' ARE grounded in source task_tools and the source step.) • ASSUMED HAZARD (safety_notes[2]): 'The e-motor module is a heavy sub-assembly - secure and chock it on the bench before applying wrench force so it cannot shift or roll.' — the source provides no weight, handling, or movement information about the module; 'heavy', 'shift or roll', and the chock/secure requirement are assumed with no basis in the source steps or tools, and this assumed hazard is what seeds the invented 'secure on bench' action in step 1.
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 145 | 9 | 145 | yes | Assembles the upgraded clutch sub-assembly that couples the diesel engine to the new e-motor for the FlexBoost hybrid conversion. Operators merge and shim the clutch housing components, drill and pin the clutch pack for anti-backout containment, install the drive plate and clutch assembly to the engine, then build out and mate the e-motor before sliding the alternator into place. This off-line module is later fed to Final Assembly. | • Heavy-load/crush hazard: the overhead crane, shackles, and choker are used to lift the clutch housing and e-motor (removing the e-motor from its crate and lifting it into the diesel engine) - keep hands clear of pinch points and never stand under a suspended load. • Stored-rotation hazard: the clutch can spin during assembly - temporary clutch lock bolts (7/16-20) must be installed to hold it before torquing and removed afterward as marked critical. • Drill press hazard at 2200 rpm with mill and drill bits plus cutting oil and compressed air: secure the workpiece, wear eye protection against hot chips/oil mist, and keep the punch set and bits clear of rotating tooling. • High-torque fastening hazard: multiple bolts torqued to 47, 54, and 108 ft-lbs with impact guns and torque wrenches - bolts and sockets can slip suddenly, so brace properly and keep a clear hand position. • Pinch hazard during mating: prying with the pry bar, installing snap rings, and sliding the alternator/e-motor onto shafts can trap fingers between mating parts - keep hands off mating faces during final seating. | no | no | • 0 operators on source task (planned_operators=0) • kept all part numbers verbatim (10, 16, 24, 27, 28, 35, 38, 39, 40, 41, 6, 13, 14, 3) • kept torque values verbatim (47, 54, 108 ft-lbs), drill speed 2200, tension pin 3/16" x 1", clutch lock bolts 7/16-20 • 9-step source structure preserved; only grammar/spelling fixed (e.g. 'Mobilegrease'->'Mobilgrease', 'ftibs'/'IBSft'->'ft-lbs') and imperative titles added • step durations already summed to 145; kept as-is • MINOR (description, not step-instruction): The description states 'This off-line module is later fed to Final Assembly.' The source never mentions 'Final Assembly' anywhere; the station/zone is 'Sub Assemblies' and step 7 only says 'Potential sub assembly'. This is an authored inference. It is permitted under the rules (grounded in standard sub-assembly project context) so it does not set invented_data, but it is the one detail in the rewrite with no explicit textual basis in the source. • NOTE (not a defect): Step 3 instruction changes source 'prevent blackout' to 'prevent backout'. This is a legitimate spelling fix (source 'blackout' is a typo for 'backout' in a containment-pin context), consistent with the rewrite's stated grammar/spelling-fix scope. • NOTE (not a defect): Safety note 3 renders the source tool 'Compressor' as 'compressed air'. This is a faithful paraphrase of an existing source tool, not invented data.
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 46 | 7 | 46 | yes | Builds the upgraded alternator sub-assembly off-line for the FlexBoost hybrid retrofit: stacks and bolts the alternator adapter, presses the bearing and snap rings, chases threads, greases and installs the insert, fits the flywheel adapter, mates the alternator to part 28 with crane support, and torques the flywheel adapter to final spec. This prepares a ready-to-install alternator module for downstream final assembly. | • Crane-assisted lift of the alternator and pilot bearing (step 6) is a heavy load - keep hands and feet clear, verify rigging, and never reach under a suspended load. • Pressing part 18 onto part 17 and driving it with a mallet (step 2) risks pinch points and a slipping/launching part - keep fingers clear of the press platen and seating edge. • Snap ring installation (step 2) with snap-ring pliers can launch the ring under spring tension - wear eye protection. • Chasing threads with the tap/die and air compressor (step 3) generates flying metal chips and high-pressure air - wear eye protection and keep the air stream away from skin. • Final torquing of the flywheel adapter to 54 ft-lbs while supporting the rotor with a leverage bar (steps 6-7) involves stored tension and a pinch hazard - maintain a firm stance and keep hands off rotating/clamping surfaces. | no | no | • 0 operators on source task (planned_operators=0) • kept all part numbers verbatim (28, 31, 17, 18, 20, 37, 36) • kept torque values verbatim (30 ft-lbs, 54 ft-lbs) and hardware spec M10x1.5x40mm / M10-1.5 • kept Mobilgrease XHP material reference verbatim • source step durations already sum to planned 46 min; preserved as-is • kept all 7 source steps; only added titles and fixed grammar/spelling (e.g. 'Toque'->'Torque', 'FTIbs'->'ft-lbs') • MINOR/grounding caveat (not invented data): Safety note 1 references 'the alternator and pilot bearing (step 6)' as the crane lift. Source step 6 says 'Use crane to lift pilot bearing and support the alternator bearing' - it lifts the PILOT BEARING (and supports the alternator BEARING), not 'the alternator and pilot bearing.' The hazard (crane-assisted heavy lift) is grounded in the source 'Crane' tool + step 6 action, so this is a wording imprecision rather than invented data. • MINOR/grounding caveat (not invented data): Step 1 title/name is 'Install alternator adapter' which matches the source step 1 name 'install Alternator Adapter'; however the rewrite's step 6 name 'Mount part 28 to alternator' and step 1 both involve 'part 28' (source step 1 = 'Part 28 to part 31'; source step 6 = 'Install part 28 onto alternator'). Part 28 appears in both source steps, so no invention - just noting the duplicate part reference is faithful to the source. • Safety note for step 3 ('high-pressure air... keep the air stream away from skin') is grounded: source step-3 tools include 'Air compressor', so the air-compressor hazard has a basis. Not flagged as invented.
Sub Assemblies | 15 | Trailer Build | 240 | 3 | 240 | yes | Build the trailer subassembly off-line in the Sub Assemblies station, providing the rolling platform onto which the completed FlexBoost hybrid power unit is later mounted during Final Assembly. This prepares, assembles, and inspects the trailer frame so it is ready to receive the genset-to-hybrid converted module. | • Positioning and joining the trailer frame is a heavy-load operation — use the crane/jig for lifts and keep hands and feet clear of swinging or descending loads to avoid crush injuries. • During frame mate-up and fastening, watch for pinch points between mating members and at clamp/jig contact points. • When torquing fasteners on a clamped or jig-held frame, the assembly can shift or release stored tension — secure the frame and stay clear of the load path. • Confirm the trailer is chocked or restrained before and after the build so it cannot roll while being worked on or moved off the jig. | YES ⚠ | no | • NO SOURCE DATA - fully authored, needs review • 0 operators on source task • Source task had 0 steps, no tools, and null description/safety notes - entire breakdown authored from task name + project context • No tools, part numbers, or spec values present in source; none invented • INVENTED TOOL: Step 1 instruction adds equipment with no basis in source (task_tools is []): 'Set up the build jig/fixture and position the crane for heavy lifts.' Neither a crane nor a jig/fixture appears anywhere in the source. • INVENTED TOOL/PART: Step 2 instruction invents specific equipment and parts: 'Lift and position the trailer frame members onto the jig using the crane' and 'fasten the frame members together with the supplied hardware.' Crane, jig, and 'supplied hardware' are not in the source (no tools, no part numbers, no steps). • INVENTED TOOL: Step 3 instruction invents jig + chocking equipment: 'Remove the trailer from the jig and chock or restrain it.' No jig or chock device is grounded in the source. • UNGROUNDED SAFETY NOTE: safety_notes assume crane/jig/clamp hazards that have no basis in any source step: 'use the crane/jig for lifts', 'watch for pinch points between mating members and at clamp/jig contact points', and 'the assembly can shift or release stored tension.' These hazards derive from invented equipment, not from source content (source has 0 steps and no tools). • CONTRADICTORY FLAG: The rewrite's own flags claim 'No tools, part numbers, or spec values present in source; none invented' and 'no tools' authored, but the step instructions introduce a crane, build jig/fixture, clamp, and 'supplied hardware' — tools/parts that are in fact invented. The flag is false.
Final Assembly | 16 | Merge Battery Pack and Chassis | 14 | 4 | 14 | yes | Lower the hybrid chassis onto the battery pack and bolt the two together to merge them into a single unit during Final Assembly. This joins the upgraded battery pack to the chassis as part of building up the finished hybrid power unit. | • Crane lift of the chassis: keep clear of the suspended load and never position hands or body beneath it while lowering onto the battery pack - crush hazard. • Battery pack and its wiring are live energy storage: confirm battery wires are clear of the joint before lowering to avoid pinching/severing conductors and electrical/stored-energy hazard. • Use the drift pin only to align holes; keep fingers out of bolt holes and alignment points during final set-down to avoid pinch/amputation as the chassis seats. • Wear ear muffs when running the impact gun to tighten the 12 bolts, per the operator note, to protect against impact-gun noise. • Remove rigging straps only after all 12 bolts are installed and the joint is secured, so the load is never released onto an unbolted assembly. | no | no | • 1 source step split into 4 logical groupings (Prep -> Lower/Align -> Bolt -> De-rig) • kept bolt spec '3/4-10 x 2" long, 12 total' and 'nut side facing up' verbatim - no specs invented • kept 'ear muffs when tightening' note verbatim from source • durations distributed proportionally to effort, sum = 14 (planned) • MINOR (not invented data, not dropped): every step is tagged "change_note":"verbatim" but no step is actually verbatim - all were reworded/reformatted, e.g. source 'lower chassis on to battery pack' -> 'Lower the chassis onto the battery pack', and 'install 3/4 - 10 x 2” long bolts 12 total' -> 'Install the 3/4-10 x 2" long bolts, 12 total.' These are allowed grammar/formatting fixes, but the 'verbatim' label is inaccurate. • BORDERLINE safety note (acceptable, flagged for transparency): note 2 calls the battery 'live energy storage' with 'electrical/stored-energy hazard.' The source only says 'Ensure Battery wires are not in the way' - it never states the pack is live/energized. The energized-battery characterization is an inference from general project context (hybrid power unit), not from the steps themselves.
Final Assembly | 17 | Install Upgraded Powertrain Module | 25 | 4 | 25 | yes | Mounts the upgraded engine and alternator powertrain module into the hybrid unit's chassis during Final Assembly and reconnects its oil, intercooler, and fuel services. This re-integrates the powertrain so the FlexBoost hybrid genset is ready for final fit-up on the trailer. | • Rigging and lowering the combined engine and alternator assembly is a heavy crane/jig lift - keep hands and body clear of the suspended load and pinch points, and never work under an unsecured load. • Removing the alternator and engine mount bolts while the assembly is rigged means it is partially supported by the crane - the load can shift or swing as bolts are released, so control the assembly before backing fasteners out. • Fuel selector and supply/return fuel lines hold residual diesel - cap or contain lines to prevent flammable fuel spills and keep ignition sources away while connecting. • Oil filter housing, oil drain, and oil lines can weep residual oil - manage spills to avoid slip hazards and skin contact. • Sealing the barb fitting with teflon using a 7/8" socket involves applying torque to a fuel/oil fitting - secure the part to avoid slipping and pinched fingers. | no | no | • 1 source step expanded into 4 logical groupings (Prep/rig -> mount -> oil & cooling -> fuel) • task_tools lists only '19mm Ratcheting wrench'; source instruction also names a 7/8" socket and teflon - kept verbatim, not added to task_tools • kept '7/8\" socket and teflon' detail verbatim from source • durations distributed proportionally to sum to planned 25 min; all steps sequential
Final Assembly | 18 | Reinstall control cabinet | 81 | 5 | 81 | yes | Reinstalls the upgraded control cabinet onto the hybrid unit during Final Assembly: bolting the cabinet to its perimeter mounts, securing the mVEC sub-assembly, fitting the wire bar, and reconnecting the full control-cabinet and engine wiring harness including the alternator/AVR leads. This restores the genset's electrical control and power-electronics connections so the converted hybrid unit can operate. | • Cabinet, ground, starter, and main battery leads carry stored electrical energy - verify the system is de-energized/disconnected before connecting cabinet and main battery leads on the starter to avoid shorts and arc/shock. • Pre-drilling with the 1/8" bit and driving self-tappers into the mVEC assembly creates sharp swarf and pinch points - keep hands clear of the bit and chips and de-burr as needed. • Removing the 24mm bolts to fit the wire bar can release fasteners under load - support the assembly and watch for pinch points when bolts are backed out. • Flush-cutting zip ties leaves sharp tie ends and the cutters are a laceration hazard - trim flush and keep fingers clear of the blade. • Reconnect alternator power, AVR, and battery leads only against their labels and to the correct terminals - mismatched high-current connections can cause electrical damage or arcing. | no | no | • merged redundant source steps 2 and 3 (both pre-drill 1/8" + install two self-tappers on mVEC) into one step; combined their 20+5 min to preserve the 81-min sum • kept 1/8" drill bit and 24mm bolt values verbatim • source step 2 and 3 listed a drill action but no drill in tools[]; did not add a drill tool • 1 operator on source task
Final Assembly | 19 | Install Telematics | 15 | 2 | 15 | yes | Install and wire the telematics unit on the finished hybrid power unit by routing its harness into the control cabinet and connecting the LTE and GPS leads to their corresponding antenna ports. This enables remote monitoring and connectivity on the converted FlexBoost hybrid genset. | • Routing the telematics wire down into the control cabinet exposes you to live cabinet wiring and stored energy from the battery/power-electronics modules - verify the cabinet is de-energized and locked out before reaching in. • Pulling the harness through cabinet openings can chafe or pinch the wire on sharp panel edges - feed it carefully to avoid insulation damage and finger pinch points. • Mis-matched antenna connections (LTE/GPS) can damage the telematics unit - confirm each lead lands on its correct port (LTE 1 to Antenna 1, LTE 2 to Antenna 2, GPS 1 to Antenna 4) before powering up. | no | no | • 0 operators on source task • no tools listed on source task or step • single source step split into 2 logical groupings (route wire / connect antennas) • kept antenna mapping verbatim: LTE 1->Antenna 1, LTE 2->Antenna 2, GPS 1->Antenna 4
Final Assembly | 20 | Install original cooling and after-treatment system | 61 | 9 | 61 | yes | Reinstalls the donor genset's original cooling assembly and DEF after-treatment system onto the hybrid unit during Final Assembly, including the radiator/cooling module, DEF tank and cover, intercooler and radiator hoses, fan shroud, and exhaust. This restores engine cooling and exhaust after-treatment so the reassembled hybrid power unit can run safely. | • Cooling assembly is lifted and set in place with a crane - stay clear of the suspended load, control the lift, and keep hands out of pinch points as it is aligned to the chassis. • Aligning the cooling assembly and seating perimeter bolts with a mallet creates struck-tool and pinch hazards - keep fingers clear of bolt holes and mating surfaces while persuading parts into alignment. • Coolant-system components (radiator hoses, intercooler hoses, coolant drain) can hold residual coolant - manage spills and avoid contact if any fluid remains in the system. • Exhaust and exhaust-valve work involves gaskets and an air line under the after-treatment system - ensure the assembly is fully cooled before handling to avoid burns and verify the valve air line is properly seated. | no | no | • Source steps 1-8 had blank titles; titles added, instructions cleaned to imperative bullets, content kept verbatim • Step 9 had empty instruction and 0 photos but 1 min duration - kept as a 1-min close-out placeholder (change_note=ADDED) to preserve the duration sum; no action invented, needs review • Kept part numbers verbatim: DEF hose 03022 (front), DEF hose 03018 (back) • Kept hardware specs verbatim: M8 x 1.25 x 25mm (DEF tank), 14x 10mm + 2x bolts (DEF cover), 13x bolts (fan shroud), 4 front screws + perimeter bolts (cooling assembly), 4x exhaust bolts • Source task_tools[] and all per-step tools[] were empty - no tools listed despite crane and mallet being mentioned in instructions • Step durations sum to 61, matching planned_duration_minutes
Final Assembly | 21 | Install V2 cooling system | 15 | 2 | 15 | yes | Installs the V2 cooling system into the finished hybrid unit during Final Assembly by mounting the coolant pump and routing the coolant hoses between the pump, e-motor, heat exchanger drain, and inverter. This completes the closed-loop cooling circuit needed to keep the upgraded power-electronics and e-motor within operating temperature on the hybrid power unit. | • Coolant hoses connect to power-electronics components (inverter) and the e-motor module; confirm the high-voltage system is de-energized and isolated before routing hoses near these connections to avoid electrical/stored-energy hazard. • Cut and fit each hose to the specified length (24", 14", 26.25") and secure all connections fully; loose or unseated hose ends can cause coolant leaks and spills, creating a slip and contamination hazard. • Verify hose routing keeps lines clear of pinch points and moving/hot assemblies (e-motor, clutch) before final securing to prevent abrasion, chafing, and a future leak. | YES ⚠ | no | • 0 operators on source task (planned_operators=0) • No tools listed on source task or step - none invented • Kept hose lengths verbatim: pump->90deg e-motor=24", pump->HE drain=14", inverter->e-motor straight kit=26.25" • Single source step split into 2 logical groupings (mount pump, route hoses) • Expanded abbreviation HE -> heat exchanger inline; no new specs added • INVENTED DATA (safety_notes[2]): "keeps lines clear of pinch points and moving/hot assemblies (e-motor, clutch)" introduces a 'clutch' component that appears nowhere in the source notes, tools, or actions. The source only references pump, e-motor, HE (heat exchanger) drain, and inverter. The clutch is a fabricated nearby-component used to assert an abrasion/chafing/heat hazard with no basis in the steps.
Final Assembly | 22 | Reinstall the panel system | 179 | 18 | 179 | yes | Reinstalls the Airmen enclosure panel system onto the hybrid unit during Final Assembly, including side panels, cross members, brackets, end panels, doors, and trim, then torques all hardware so panels sit flush. This re-skins the converted genset, restoring its protective enclosure and re-establishing the E-Stop circuit on the cab side. | • Panel 6 is rigged with 3 eye hooks and strapping, and the cross member is picked with a crane - keep hands clear of the load path and suspended panels to avoid crush and pinch injuries. • Hardware is started loosely and only fully torqued at the end - panels and cross members can shift or drop until tightened, so support them and watch for pinch points while aligning to the engine-side and chassis alignment pins. • Final tightening uses impact guns and 24mm/13mm sockets and wrenches - wear eye protection and keep fingers clear of rotating tools and the hardware as it seats. • The cab-side end panel work connects the E-Stop - confirm the safety circuit is correctly reconnected and functional before the unit is energized. • Work is performed around the diesel engine, fuel line bracket, oil filter bracket, and exhaust hanger - avoid hot surfaces and do not damage fuel or oil lines while routing panels and brackets. | no | no | • Source had many well-structured steps (18); kept structure 1:1, fixed grammar/spelling and added imperative titles only - no regrouping • Step durations already summed to planned 179 min; preserved verbatim • Kept panel/part references verbatim: Airmen panels 1-6, panels 3-5, V2 cooling, M8 bolts • Step 9 contains an embedded out-of-order dependency (oil filter bracket must be added to the cross member before step 5 installs it); preserved as a note rather than physically reordering to keep source numbering • Normalized 'airmen'/'airment' spelling to 'Airmen' across steps • Source steps carried no per-step tools except steps 5 and 11; task_tools list (24mm/13mm sockets & wrenches, 3/8" impacts) reflected only in the tightening step instruction, no tools invented
Final Assembly | 23 | Fluid Replenishment | 30 | 3 | 30 | yes | Refills the hybrid unit's operating fluids during Final Assembly, replacing what was drained during donor genset teardown so the reassembled diesel-and-battery hybrid is ready for commissioning. Ensures the engine, cooling system, and DEF after-treatment system are filled to operating levels before the unit leaves the line. | • Engine oil, coolant, and DEF are slippery and can cause slip hazards if spilled; contain and clean up any spills immediately. • Open coolant and engine systems only when cool — residual heat or pressure in the cooling system can cause hot-fluid burns. • DEF (Diesel Exhaust Fluid) is corrosive to skin, eyes, and many metals; wear gloves and eye protection and avoid contaminating other fluid systems. • Handle and store fluids per their SDS and dispose of any waste or overflow as regulated fluid waste, not general trash. | YES ⚠ | no | • NO SOURCE DATA - fully authored, needs review • 0 source steps; task_tools empty; existing_description and existing_safety_notes null on source task • Fluids (engine oil, coolant, DEF) inferred from project context (diesel-hybrid genset, drained during disassembly); no fluid types, capacities, or part numbers given in source • Durations authored to sum to planned 30 min • INVENTED DATA (materials): Source task has step_count 0, steps [] and task_tools []. The rewrite invents specific fluids/materials in step instructions with no source basis: step 1 'Stage the required operating fluids (engine oil, coolant, DEF after-treatment fluid)'; step 2 'Add engine oil through the oil fill', 'Fill the cooling system with coolant', 'Fill the DEF after-treatment tank'. No fluid types appear anywhere in the source. • INVENTED DATA (tool): Step 1 instruction adds a tool 'and a clean funnel at the work area.' The source task_tools array is empty; no funnel is listed. • INVENTED DATA (physical actions): All step instructions are fabricated actions absent from the source (which has zero steps). Examples: step 1 'Locate and open the engine oil fill, coolant fill, and DEF fill points; wipe each fill area clean'; step 2 'checking the level until it reaches the operating mark' and 'watching for trapped air'; step 3 'Reinstall and secure all fill caps' and 'confirm no leaks at the fill points.' None of these actions exist in the source notes. • INVENTED DATA (spec-like target values): Step 2 references filling 'to the operating mark' and 'to its operating level'; step 3 'Recheck each fluid level (oil, coolant, DEF)'. These operating-level/fill targets are authored with no source capacities, levels, or marks given. • SAFETY NOTES assume hazards with no basis in any step (source has zero steps): 'Engine oil, coolant, and DEF are slippery and can cause slip hazards', 'residual heat or pressure in the cooling system can cause hot-fluid burns', 'DEF (Diesel Exhaust Fluid) is corrosive to skin, eyes, and many metals'. These hazards derive entirely from the invented fluids, not from source actions. • NOTE (not penalized): The rewrite's own flags honestly disclose this is fully authored with no source data ('NO SOURCE DATA - fully authored, needs review'; 'Fluids ... inferred from project context ... no fluid types, capacities, or part numbers given in source'). The description and safety_notes framing are arguably grounded in general project context (diesel-hybrid genset), but the step INSTRUCTIONS go beyond titles/description and fabricate concrete tools, materials, and physical actions, which the audit rule treats as invented data.
Final Assembly | 24 | Install hybrid unit on trailer | 30 | 4 | 30 | yes | Mounts the assembled FlexBoost hybrid power unit onto its trailer as the final step of Final Assembly, producing the trailer-mounted finished unit. No operator notes were recorded on the source step, so this breakdown is fully authored from the task name and project context and requires shop-floor review before use. | • Lifting the hybrid power unit onto the trailer is a heavy-load lift; keep hands and body clear of the load path and pinch points while it is suspended and being lowered into place. • Position and chock the trailer before lifting; an unsecured or unbraked trailer can roll or shift under the weight of the unit being lowered onto it. • Confirm the unit is fully fastened/secured to the trailer before releasing the lift; an unsecured load can tip or slide off the trailer. • The hybrid unit contains battery and power-electronics modules; treat it as energized and avoid impact or pinching of cabling during placement. | YES ⚠ | no | • NO SOURCE DATA - fully authored, needs review • source step 1 has empty name and empty instruction • 0 tools on source task and source step (crane/jig referenced from project context only) • durations authored to sum to planned 30 min • INVENTED TOOL: Step 2 instruction 'Rig the assembled hybrid power unit to the crane/jig and lift it' introduces a crane/jig. Source task_tools is [] and the single source step's tools is [] — no crane or jig appears anywhere in the source. The rewrite's own flags concede this: '0 tools on source task and source step (crane/jig referenced from project context only)'. A specific lifting tool in a step instruction with no source basis is invented data. • INVENTED TOOL/EQUIPMENT: Step 3 instruction 'release and remove the lift rigging' depends on the same fabricated crane/jig rigging; 'lift rigging' is equipment absent from the source (empty tool lists). • INVENTED ACTION/EQUIPMENT: Step 1 instruction 'chock/brake it so it cannot roll' introduces chocks/brakes — specific equipment and an action with no basis in the source step (source step name and instruction are both empty strings). • SAFETY NOTE WITHOUT BASIS: 'The hybrid unit contains battery and power-electronics modules; treat it as energized and avoid impact or pinching of cabling during placement.' assumes battery/power-electronics/energization and cabling hazards. The source step is empty (no instruction, no tools) and no source action mentions batteries, energization, or cabling; this hazard is asserted beyond the source actions. • FULLY AUTHORED FROM EMPTY SOURCE: The source step has name='' and instruction='' with planned_duration_minutes=30. All four rewrite steps and every physical action in their instructions (rig, lift, lower onto mounting points, fasten, verify seating) are authored, not derived from any source action. The rewrite acknowledges this ('NO SOURCE DATA - fully authored, needs review'), but the step-level instructions still assert specific actions/tools the source does not contain.

## Steps
Station | WBS | Task | Step # | Step title (NEW) | Step instruction (NEW) | Min | Concurrent | Change
Disassembly | 1 | Fluid Drain and Labeling | 1 | Prepare for drain | - Remove radiator cap to improve flow - Attach drain hose to the drain port - Position collection bucket under the outlet | 3 |  | reordered
Disassembly | 1 | Fluid Drain and Labeling | 2 | Drain fluid into bucket | - Drain fluid into the bucket until flow stops | 12 |  | verbatim
Disassembly | 1 | Fluid Drain and Labeling | 3 | Label generator panels | - While the fluid drains, label the generator panels so they can be identified later for reinstall | 0 | yes (0 min) | clarified
Disassembly | 2 | Panel Removal | 1 | Remove panels | - Remove the panels using the sockets and impact guns (panels are not yet labeled, so identify them by location). | 25 |  | verbatim
Disassembly | 2 | Panel Removal | 2 | Store hardware in correct areas | - Place the hardware in the correct storage areas; correct hardware storage is critical for reassembly. | 5 |  | split
Disassembly | 2 | Panel Removal | 3 | Sort panels onto carts in sequence | - Place the panels on the cart based on their use. - Arrange the panels on the carts in the specified sequence. | 5 |  | merged
Disassembly | 3 | Remove Control Cabinet | 1 | Disconnect cabinet wiring | - Remove alternator wires - Remove wire harness - Remove starter solenoid wire | 12 |  | reordered
Disassembly | 3 | Remove Control Cabinet | 2 | Disconnect sensors and grounds | - Disconnect fuel level and containment level sensors - Remove ground wire on engine side - Remove wire harness bar | 10 |  | reordered
Disassembly | 3 | Remove Control Cabinet | 3 | Remove base cabinet bolts | - Remove base cabinet bolts | 8 |  | reordered
Disassembly | 4 | Remove Cooling and After-Treatment Components | 1 | Disconnect fuel valve and ground | - Remove the fuel valve system - Remove the ground from the engine block to the fuel tank | 8 |  | reordered
Disassembly | 4 | Remove Cooling and After-Treatment Components | 2 | Remove cooling components | - Remove the intercooler flanges - Remove the fan shroud | 9 |  | reordered
Disassembly | 4 | Remove Cooling and After-Treatment Components | 3 | Remove DEF cooling lines | - Remove the engine-block DEF cooling lines - Note line markers: 03022 front, 03018 back | 8 |  | merged
Disassembly | 4 | Remove Cooling and After-Treatment Components | 4 | Remove DEF tank | - Remove the DEF tank (plan to keep this on the unit) | 5 |  | verbatim
Disassembly | 5 | Remove Engine / Alternator Module | 1 | Disconnect drains, lines and ground | - Remove the oil drain from the tank. - Remove the zip ties securing the oil lines to the chassis. - Remove the external fuel drains. - Remove the fuel line zip ties. - Remove the grounding wire. | 8 |  | reordered
Disassembly | 5 | Remove Engine / Alternator Module | 2 | Remove cross pipe, shroud and mount hardware | - Remove the intercooler cross pipe. - Remove the alternator fan shroud. - Remove the top alternator mount bolts. - Remove the oil filter housing bolts, but leave the oil filter housing in place. | 8 |  | reordered
Disassembly | 5 | Remove Engine / Alternator Module | 3 | Rig and lift engine to jig | - Lift the engine. - Leave the rigging in the engine for the transfer to the jig. | 4 |  | verbatim
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 1 | Install external fuel tank fittings | - Install the external fuel tank fittings. | 5 |  | verbatim
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 2 | Transfer mounts to new chassis | - Transfer the alternator mounts to the new chassis. - Transfer the engine mounts to the new chassis. - Critical: loosen the motor mount screws while loaded - this will help remove them. | 13 |  | split
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 3 | Free and lift out fuel tank | - Load up the fuel tank. - Remove the perimeter fuel tank bolts. - Remove the shipping blocks. - Lift the chassis from the containment tank. - Remove the perimeter strap nuts. - Loosen the top strap nuts. - Lift the fuel tank to prevent fuel from leaking. - Remove the fuel tank hose. | 18 |  | split
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 4 | Rework fuel hose and reinstall tank | - Rotate the barb on the tank 180 degrees. - Add 11 ft of 3/8" fuel hose. - Rotate the fuel tank inside the containment tank. - Install the new fuel line, ensuring it does not get pinched. - Reinstall the tank straps. | 16 |  | split
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 5 | Refit chassis onto fuel tank | - Bring the chassis back over. - Drop the chassis onto the new fuel tank. - Reinstall the perimeter bolts, using the crane to adjust your location. | 16 |  | split
Disassembly | 6 | Remove Fuel Tank, Flip and Prep Chassis | 6 | Install end mesh cover | - Install the end mesh cover. | 5 |  | verbatim
Sub Assemblies | 7 | Battery Build | 1 | Stage battery components and tools | - Gather the battery pack components and required hardware at the Sub Assemblies station. - Confirm the 1 1/8" socket and supporting tools are available before starting. | 0 |  | ADDED
Sub Assemblies | 7 | Battery Build | 2 | Assemble battery pack | - Position and join the battery pack components into the upgraded module. - Install and tighten the fasteners using the 1 1/8" socket. | 0 |  | ADDED
Sub Assemblies | 7 | Battery Build | 3 | Inspect and stage completed pack | - Verify the assembled battery pack is complete and secure. - Stage the finished module for transfer to Final Assembly. | 0 |  | ADDED
Sub Assemblies | 8 | Panel rework station | 1 | Rework Panel 4: transfer accessories and install foam | - Remove accessories from Panel 4. - Remove the hinges. - Remove the louver box. - Remove the accessories plate. - Remove the bump stop. - Move the old panel to the service parts bin. - Get the updated Panel 4. - Reinstall the bump stops. - Reinstall the accessories plate. - Reinstall the hinges. - Install foam on the bottom edge of the louver. - Install 1466 foam to the top panel. - Install 1467 foam to the bottom panel. | 16 |  | verbatim
Sub Assemblies | 8 | Panel rework station | 2 | Rework Panel 10: transfer accessories and install foam | - Remove the baffle box from Panel 10. - Remove the door handle. - Remove the door hinges. - Reinstall the door handles. - Reinstall the hinges. - Install the baffle foam. - Install the baffle box. - Drill out the baffle screw hole with the step bit if it is not aligned. - If the weldstud is missing, disregard. - Install the blocker plate with two nuts and two self tappers. - Install foam 1646 (can be installed first if needed). - Install 1469. - Install 1470. - Install 1468. - Install the perimeter gasket, starting from the bottom perimeter and working around the door. | 30 |  | verbatim
Sub Assemblies | 8 | Panel rework station | 3 | Rework Panel 11: transfer accessories and install foam | - Remove the baffle box from Panel 11. - Remove the hinges. - Get the new panel. - Install the hinges. - Install the baffle foam first. - Install the lower baffle foam. - Install the baffle. - Drill out the holes if needed. - Install the side plate. - Install the baffle nuts. - Install the handle. - Install foam 1457. - Install foam 1458. - Install foam 1459. - Install the perimeter gasket. | 33 |  | verbatim
Sub Assemblies | 8 | Panel rework station | 4 | Rework Panel 9: transfer accessories and install foam | - Remove the hinges from Panel 9. - Remove the baffle box. - If the baffle box has foam on the edges, remove it with a scraper. - Remove the handle, ensuring the gasket comes off with the handle. - Get the new door. - Install the door hinges. - Install the handle. - Install foam 1645. - Install the lower baffle seal and press it in place. - Install the baffle box, drilling holes if necessary. - Install the side plate. - Install the baffle box nuts. - Install the side plate self tappers (may need to drill through rivets, which is okay here). - Install foam 1457. - Install foam 1458. - Install foam 1459. - Install the perimeter gasket. | 30 |  | verbatim
Sub Assemblies | 8 | Panel rework station | 5 | Rework Panel 3: transfer accessories and install foam | - Remove the interior door hinges from Panel 3. - Remove the exterior hinges. - Remove the bumpers. - Get the new panel. - Install the interior hinges. - Install the exterior hinges. - Install foam 1456. - Install foam 1477. - Install the perimeter foam seal on the inside door. | 15 |  | verbatim
Sub Assemblies | 8 | Panel rework station | 6 | Rework Panel 6: install foam and prep | - Install the edge foam gasket on the outer edge of the bolts on Panel 6. - Install the side foam inside of the rivet hole. - Install the radiator cover plate but leave access to fill. - Install foam 1463 first (x2). - Install foam 1475. - Install foam 1476. | 18 |  | verbatim
Sub Assemblies | 8 | Panel rework station | 7 | Rework Panel 5: install foam and prep | - Panel 5 is part of the cooling stack. - Install 1460. - Install 1461. - Install 1462. - Install 1464. - Install 1465. - Install 1473. - Install 1474. - Install 1472. - Install 1471. | 30 |  | verbatim
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 1 | Fit foam to V2 cooling assembly | - Grab part 1300 (V2 cooling assembly). - Install foam 1478. - Install foam 1479. - Install foam 1480. | 5 |  | verbatim
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 2 | Mount part 1300 and fans on panel 5 | - Start with part 1300 with foam panels. - Add foam seal to the bottom. - Punch holes in the foam seal to allow bolts to pass through. - Install part 1300 onto panel 5. - Install fans part 31 onto part 1300. - Use part number 5; chase threads if needed. | 30 |  | split
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 3 | Install reservoir and radiator on panel 3 | - Install reservoir part 27 with part 3. - Install foam gasket part 35 onto panel 3. - Widen all radiator holes with a step bit, then install radiator part 19 onto panel 3, ensuring the two radiator bolts are on top. - Use part 3 with 7/16” washers to install the radiator. - Install foam tape on panel 3 for the air duct. - Install foam seal on the radiator. | 30 |  | split
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 4 | Remount part 1300, cooling tower and inverter | - Bring part 1300 onto panel 3 (amended); ream out the holes in part 1300. - Install with M6 x 30 and 7/16” washer. - Chase all threads on part 1300. - Install the cooling tower to panel 3 using part 3 with nuts and 7/16” washer. - Install inverter part 33 to part 32 using M6 x 15mm. - Install the inverter component on the cooling tower with M6 x 30mm; it will sit proud on the bracket. | 30 |  | split
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 5 | Plumb drain system and coolant hoses | - Install radiator plug part 21 with a 3/4” hex socket. - Install drain system parts 22, 20, 16, 17. - Apply Teflon between parts 16 and 17. - Install parts 28 and 20 onto the radiator (orientation is important). - Install parts 24, 23, 25, 26. - Install the radiator hose with two hose clamps part 13 and part 18. - Install the inverter coolant hose adapter. - Install the inverter 3/4” hose part 15. - Use part 30 worm clamps. | 35 |  | split
Sub Assemblies | 9 | Assemble V2 Cooling System with Panel | 6 | Release radiator stop and move assembly to panel 5 | - Remove the radiator stop. - Move the complete assembly to panel 5. - If needed, keep the top bolts loose for the air inlet and radiator body bolts. | 10 |  | split
Sub Assemblies | 10 | mVEC / DC-DC Converter Build | 1 | Mount components to brackets | - Mount the mVEC relay box to its bracket. - Mount the DC-DC converter to its bracket. | 20 |  | verbatim
Sub Assemblies | 10 | mVEC / DC-DC Converter Build | 2 | Add wiring harness | - Add the wiring harness to the assembly. | 20 |  | verbatim
Sub Assemblies | 11 | Upgrade Control Cabinet | 1 | Mount DIN rail and Tinkerer | - Install the DIN rail with 2x self-tappers. - Mount the Tinkerer and lock it in place with DIN locks. | 30 |  | verbatim
Sub Assemblies | 11 | Upgrade Control Cabinet | 2 | Install 480V contactor and CAN-bus junction | - Install the 480V contactor. - Install the CAN-bus junction. | 35 |  | verbatim
Sub Assemblies | 11 | Upgrade Control Cabinet | 3 | Wire Tinkerer harness | - Install the wire harness for the Tinkerer. - Install the resistor between A and B. - Install the harness points to the CAN-bus. | 30 |  | verbatim
Sub Assemblies | 11 | Upgrade Control Cabinet | 4 | Install mVEC harness | - Install the mVEC 12V and CAN harness 1604. - Route it to the front of the control cabinet. - Connect the CAN-bus connector. - Install the ground. - Install the control switch pin. - Install pin 3. | 1 |  | verbatim
Sub Assemblies | 11 | Upgrade Control Cabinet | 5 | Install DC2DC harness | - Install the DC2DC 12V harness and route it to the front of the control cabinet. - Install the CAN-bus connector. - Install the control switch. | 23 |  | verbatim
Sub Assemblies | 11 | Upgrade Control Cabinet | 6 | Install FlexBoost main harness | - Move to final assembly. - Install the FlexBoost main harness (possibly install on the cooling system first). - Connect the fan connectors, inverter connector, pump connectors, e-motor connector, and clutch and resistor. - Install the main harness ground with the engine ground. - On the control cabinet side, install the CAN 1 port. - Install the 480V 12V signal. | 34 |  | verbatim
Sub Assemblies | 12 | Build E-Motor Assembly | 1 | Stage e-motor and coolant fittings | - Secure the e-motor module on the bench and gather the elbow and straight coolant fittings. - Lay out the 26mm socket, 1/2" ratchet, crescent wrench, and 1" socket. | 9 |  | ADDED
Sub Assemblies | 12 | Build E-Motor Assembly | 2 | Install elbow coolant fitting | - Install the elbow coolant fitting first. | 18 |  | verbatim
Sub Assemblies | 12 | Build E-Motor Assembly | 3 | Install straight coolant fitting | - After the elbow is in, install the straight coolant fitting. | 18 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 1 | Merge and torque housing parts 28 and 38 | - Merge part 28 and part 38. - Align the clutch cables and the two holes so the cable comes out of the port. - Use part 10 as the hardware. - Torque to 47 ft-lbs. | 6 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 2 | Separate, grease, and shim part 35 | - Split part 35 apart (containment action for a loose bolt); use a flathead screwdriver to separate. - Apply Mobilgrease XHP to the part 35 shaft. - Wipe off the area around the base of the shaft on part 35 and the clutch side on part 38. - Torque hex bolt part 24 to 108 ft-lbs. - Install a small shim between part 39 and part 35. - Install temporary clutch lock bolts (7/16-20) to hold the clutch in place and prevent spinning. - Critical: remove the clutch lock bolts when done. | 22 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 3 | Drill and pin clutch pack bolt | - Add a pin to the clutch pack bolt to prevent backout (containment action step). - Set the drill speed to 2200. - Make the first drill pass with a mill bit. - Make the second drill pass with a drill bit, drilling through the shaft. - Install a 3/16" x 1" tension pin into the drilled hole. | 31 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 4 | Install clutch pin drive plate to engine | - Install the clutch pin drive plate onto diesel engine part 35. - Torque all bolts to 54 ft-lbs. - Torque in a star pattern. | 10 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 5 | Install clutch assembly | - Install the clutch assembly. - Use part 6 for the bolt to the engine side with locking washers. - Install part 27 on the top two bolts. - Torque bolts in a star pattern to 54 ft-lbs. | 15 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 6 | Install part 16 to clutch assembly | - Install part 16 with bolts (part 24) onto the clutch assembly. - Use a 3/8" hex socket. - Torque to 108 ft-lbs. | 5 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 7 | Build out e-motor with plates | - Potential sub-assembly: e-motor with plates. - Remove the e-motor from the crate with the shackle kit. - Use part 13 bolts to attach part 41 to e-motor part 14. - Keep note of the clocking direction; the top two bolt areas should match. - Torque to 54 ft-lbs in a star pattern. - Install part 40 to the back of the e-motor using part 3 bolts. - Torque to 54 ft-lbs in a star pattern. | 26 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 8 | Mate e-motor to diesel engine | - Install the insert with grease. - Install the shaft into the e-motor. - Install the snap rings. - Lift the e-motor into the diesel engine. | 15 |  | verbatim
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 9 | Slide alternator to e-motor | - Slide the alternator to the e-motor. | 15 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 1 | Install alternator adapter | - Build the alternator stack, joining part 28 to part 31. - Install the 8 bolts and torque to 30 ft-lbs. | 10 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 2 | Press bearing and install snap rings | - Press part 18 onto part 17 using the press. - Use a mallet to drive part 18 past the edge as needed. - Install snap ring part 20. - Flip part 17 over and install snap ring part 37. | 1 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 3 | Chase threads | - Chase the threads out with the M10-1.5 tap and die. - Use the air compressor to clear debris. | 5 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 4 | Install greased insert | - Install insert part 36 with Mobilgrease XHP. | 5 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 5 | Install flywheel adapter | - Install the flywheel adapter onto the alternator side using M10x1.5x40mm bolts. - Start all bolts before tightening down. - Use new hardware only, with the existing lock washers. | 10 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 6 | Mount part 28 to alternator | - Install part 28 onto the alternator. - Use the crane to lift the pilot bearing and support the alternator bearing. - Start two bolts to seat part 28. - Install the remaining bolts and torque to 54 ft-lbs. | 10 |  | verbatim
Sub Assemblies | 14 | Assemble Upgraded Engine / Alternator Module | 7 | Final-torque flywheel adapter | - Torque the alternator flywheel adapter to 54 ft-lbs. - Support the rotor with a leverage bar while torquing. - Mark each bolt with a wax pen. | 5 |  | verbatim
Sub Assemblies | 15 | Trailer Build | 1 | Stage trailer components and jig | - Move the trailer frame members, hardware, and required components into the Sub Assemblies work area. - Set up the build jig/fixture and position the crane for heavy lifts. - Verify all parts are present and the work area is clear before starting. | 50 |  | ADDED
Sub Assemblies | 15 | Trailer Build | 2 | Assemble and fasten trailer frame | - Lift and position the trailer frame members onto the jig using the crane. - Mate and fasten the frame members together with the supplied hardware. - Build up the trailer to its assembled configuration on the fixture. | 120 |  | ADDED
Sub Assemblies | 15 | Trailer Build | 3 | Inspect and release trailer | - Inspect the completed trailer assembly for correct fit-up and secure fasteners. - Remove the trailer from the jig and chock or restrain it. - Stage the finished trailer for transfer to Final Assembly. | 70 |  | ADDED
Final Assembly | 16 | Merge Battery Pack and Chassis | 1 | Rig chassis to crane and clear wires | - Connect the chassis to the crane. - Ensure the battery wires are not in the way. | 3 |  | verbatim
Final Assembly | 16 | Merge Battery Pack and Chassis | 2 | Lower and align chassis onto battery pack | - Lower the chassis onto the battery pack. - Continue lowering the unit until you can use the drift pin to set the alignment point. | 4 |  | verbatim
Final Assembly | 16 | Merge Battery Pack and Chassis | 3 | Install and tighten the 12 bolts | - Install the 3/4-10 x 2" long bolts, 12 total. - Ensure the nut side is facing up. - Wear ear muffs when tightening. | 6 |  | verbatim
Final Assembly | 16 | Merge Battery Pack and Chassis | 4 | Remove rigging straps | - Remove the rigging straps. | 1 |  | verbatim
Final Assembly | 17 | Install Upgraded Powertrain Module | 1 | Rig and remove mount bolts | - Rig up the engine and alternator assembly with the crane/jig - Remove the alternator and engine mount bolts | 6 |  | verbatim
Final Assembly | 17 | Install Upgraded Powertrain Module | 2 | Position and lower powertrain onto mounts | - Move the engine over, line up the engine mounts, and lower it into place - Line up the alternator mounts - Install all mount nuts | 8 |  | merged
Final Assembly | 17 | Install Upgraded Powertrain Module | 3 | Reconnect oil and intercooler services | - Install the lower intercooler hose bolts - Install the oil filter housing - Install the oil drain - Zip tie the oil lines to the chassis bar | 6 |  | merged
Final Assembly | 17 | Install Upgraded Powertrain Module | 4 | Reconnect fuel system | - Install the fuel selector on the chassis - Reinstall the fuel supply and return lines - Install the barb with a 7/8" socket and teflon | 5 |  | merged
Final Assembly | 18 | Reinstall control cabinet | 1 | Bolt cabinet and install ground | - Install the perimeter control cabinet bolts. - Install the ground wire. - Reuse the existing hardware. | 6 |  | verbatim
Final Assembly | 18 | Reinstall control cabinet | 2 | Secure mVEC self-tappers | - Install the self-tappers on the mVEC sub-assembly. - Pre-drill with the 1/8" drill bit. - Install the two self-tappers. | 25 |  | merged
Final Assembly | 18 | Reinstall control cabinet | 3 | Fit wire bar | - Remove the 24mm bolts and install the wire bar. | 5 |  | verbatim
Final Assembly | 18 | Reinstall control cabinet | 4 | Reconnect wiring harness | - Unwrap the wiring harness and begin reconnecting. - Install the ground on the intake side. - Install the starter solenoid wire. - Zip-tie the wire harness to help with strain relief. - Install the cabinet and main battery leads on the starter. - Install the insulation boot. - Install the fuel sender wire. - Install the containment overflow connector. - Finish zip-tying to the wire bar. - Install the control cabinet harness main. - Move to the other side and start on the end harness. - Install the DEF harness connectors. - Install the air pump connector. - Install the exhaust valve connector. - Install the charge air temp sensor. - Install the mass air flow sensor. - Install the inlet air temp sensor. - Install the electric fuel pump connector. - Install the EGR valve connector. - Install the alternator connector. - Install the alternator power connector. - Install the crankcase pressure sensor. - Zip-tie the harness. | 35 |  | verbatim
Final Assembly | 18 | Reinstall control cabinet | 5 | Connect alternator wires and AVR | - Install the alternator wires; they are all labeled and should be matched accordingly. - Connect the AVR. | 10 |  | verbatim
Final Assembly | 19 | Install Telematics | 1 | Route wire into control cabinet | - Pull the telematics wire down into the control cabinet. | 6 |  | split
Final Assembly | 19 | Install Telematics | 2 | Connect antenna leads | - Connect LTE 1 to Antenna 1. - Connect LTE 2 to Antenna 2. - Connect GPS 1 to Antenna 4. | 9 |  | split
Final Assembly | 20 | Install original cooling and after-treatment system | 1 | Lift cooling assembly into place with crane | - Install the cooling assembly using the crane. - Lift and set it in place. | 3 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 2 | Align cooling assembly and bolt to chassis | - Align the cooling assembly with the chassis. - Align the DEF tank. - Install the 4 front screws. - Install all perimeter cooling-assembly bolts. - Use a mallet if needed to line up the bolts. - Reuse the hardware from Disassembly. | 16 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 3 | Install DEF tank | - Install the DEF tank. - Use M8 x 1.25 x 25mm hardware. | 3 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 4 | Install DEF cover | - Install the DEF cover. - Install the 14x 10mm bolts. - Install the 2x bolts underneath. | 5 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 5 | Install intercooler hoses | - Install the lower intercooler hose. - Tighten the crossover pipe bolts. - Install the upper intercooler hose. | 4 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 6 | Install radiator and DEF hoses and coolant drain | - Install the upper radiator hose. - Install the lower radiator hose. - Install the front-side DEF hose 03022. - Install the back-side DEF hose 03018. - Install a zip tie on the lower radiator hose and trim it. - Install the coolant drain. | 9 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 7 | Install fan shroud | - Install the fan shroud. - Install one corner bolt. - Install the opposite-side corner bolt. - Install the remaining 13x bolts. | 9 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 8 | Install exhaust | - Install the exhaust. - Install the exhaust valve with gaskets. - Install the 4x exhaust bolts from front to back. - Install the valve air line. | 11 |  | verbatim
Final Assembly | 20 | Install original cooling and after-treatment system | 9 | Final close-out | - Complete the cooling and after-treatment installation (source step had no instruction text). | 1 |  | ADDED
Final Assembly | 21 | Install V2 cooling system | 1 | Mount coolant pump | - Install the coolant pump in its mounting position. | 5 |  | split
Final Assembly | 21 | Install V2 cooling system | 2 | Route and connect coolant hoses | - Install the coolant hoses between the pump, e-motor, heat exchanger drain, and inverter. - Fit the hose from the pump to the 90-degree e-motor connection at 24". - Fit the hose from the pump to the HE (heat exchanger) drain at 14". - Fit the inverter-to-e-motor straight kit hose at 26.25". | 10 |  | split
Final Assembly | 22 | Reinstall the panel system | 1 | Install Airmen panel 1 | - Install Airmen panel 1. - Install M8 bolts loosely. - Reuse existing hardware. | 2 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 2 | Install Airmen panel 2 | - Install Airmen panel 2. | 6 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 3 | Install cross bar on DEF side | - Install the cross bar on the DEF side. | 4 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 4 | Install panel 6 | - Install panel 6. - Rig the panel using 3 eye hooks with strapping. - Align to the alignment pins located by the diesel engine and on the sides; ensure they are aligned. - Install bolts loosely. | 11 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 5 | Install cross member | - Pick the cross member with the crane. - Loosen the top cross member bolts with the 24mm. - Install the chassis bolts for the cross member loosely. | 11 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 6 | Install panel 4 | - Install panel 4. - Install bolts loosely. | 6 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 7 | Install panels 3-5 / V2 cooling assembly | - Install panels 3-5 or the V2 cooling assembly systems. | 15 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 8 | Install fuel line bracket | - Install the fuel line bracket. | 3 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 9 | Install oil filter bracket | - Install the oil filter bracket. - Note: add this bracket to the cross member before installing the cross member. | 2 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 10 | Install Airmen panel cross member by controls | - Install the Airmen panel cross member by the controls. - Install loosely. | 7 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 11 | Tighten all panel hardware | - Tighten all installed panel hardware. - Make panels flush on the outside, then tighten. - Tighten the cross member bolts. - Tighten the oil filter housing bracket. | 19 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 12 | Install exhaust hanger extension bracket | - Install the exhaust hanger extension bracket. | 7 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 13 | Install air cleaner assembly | - Install the air cleaner assembly. - Reuse existing hardware. | 4 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 14 | Install Airmen DEF-side end panels | - Install the Airmen DEF-side end panels. | 9 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 15 | Install cab-side end panels and connect E-Stop | - Install the cab-side Airmen end panels. - Connect the E-Stop. | 21 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 16 | Install doors | - Install the doors. | 5 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 17 | Install cover grommets | - Install the cover grommets. | 2 |  | verbatim
Final Assembly | 22 | Reinstall the panel system | 18 | Install door trim panels and grommet | - Install the top door trim panel. - Install the grommet. - Install the bottom door trim panel. | 45 |  | verbatim
Final Assembly | 23 | Fluid Replenishment | 1 | Stage fluids and prep fill points | - Confirm the unit is on the trailer, level, and the engine/cooling systems are cool before adding any fluid. - Stage the required operating fluids (engine oil, coolant, DEF after-treatment fluid) and a clean funnel at the work area. - Locate and open the engine oil fill, coolant fill, and DEF fill points; wipe each fill area clean to prevent contamination. | 8 |  | ADDED
Final Assembly | 23 | Fluid Replenishment | 2 | Fill operating fluids to level | - Add engine oil through the oil fill, checking the level until it reaches the operating mark. - Fill the cooling system with coolant to the correct level, watching for trapped air. - Fill the DEF after-treatment tank to its operating level, taking care not to overfill or cross-contaminate with other fluids. | 16 |  | ADDED
Final Assembly | 23 | Fluid Replenishment | 3 | Verify levels and close fill points | - Recheck each fluid level (oil, coolant, DEF) and top off as needed. - Reinstall and secure all fill caps. - Wipe down fill areas, contain and clean up any spills, and confirm no leaks at the fill points. | 6 |  | ADDED
Final Assembly | 24 | Install hybrid unit on trailer | 1 | Position and prep trailer | - Position the trailer in the Final Assembly mounting area and chock/brake it so it cannot roll. - Confirm the trailer mounting points are clear and ready to receive the hybrid unit. | 6 |  | ADDED
Final Assembly | 24 | Install hybrid unit on trailer | 2 | Lift and lower unit onto trailer | - Rig the assembled hybrid power unit to the crane/jig and lift it. - Move the unit over the trailer and lower it onto the trailer mounting points, keeping clear of the load path. | 12 |  | ADDED
Final Assembly | 24 | Install hybrid unit on trailer | 3 | Secure unit to trailer | - Fasten the hybrid unit to the trailer mounting points. - Once fastening is complete and the unit is supported, release and remove the lift rigging. | 8 |  | ADDED
Final Assembly | 24 | Install hybrid unit on trailer | 4 | Verify installation | - Verify the unit is correctly seated and securely fastened to the trailer. - Confirm no cabling is pinched and the work area is clear. | 4 |  | ADDED

## Original (reference)
Station | WBS | Task | Planned min | Orig. steps | Photos | Original notes (verbatim) | Tools (source)
Disassembly | 1 | Fluid Drain and Labeling. | 15 | 1 | 7 | - Drain fluid using bucket - add hose to drain - remove radiator cap for better flow
Disassembly | 2 | Panel Removal | 35 | 1 | 18 | - Remove panels - In future we will have them labeled - Place panels on cart based on there use. - Its critical to place hard ware in correct storage areas - Panels will be places in a specific sequence on carts | 13mm Socket, 3/8" impact gun, short 13mm Socket, 3/8" Angled electric impact, 10mm Socket, 24mm socket, 1/2" impact gun
Disassembly | 3 | Remove Control Cabinet | 30 | 1 | 16 | -Remove Base Cabinet bolts - Remove Alternator wires - Remove wire harness - disconnect fuel level and containment level sensors - Remove ground wire on engine side - Remove wire harness bar - Remove starter solenoid wire
Disassembly | 4 | Remove Cooling and After Treatment | 30 | 1 | 16 | - Remove intercooler flanges - remove fuel valve system - removing fan shroud - remove engine block def cooling lines - 03022 front - 03018 back - remove ground from engine block to fuel tank - remove Def tank - we will try to keep this on the unit | 10mm wrench
Disassembly | 5 | Remove Engine / Alternator Module | 20 | 1 | 16 | - Remove oil drain from from tank - remove zip ties from oil lines to chassis - remove intercooler cross pipe - remove external fuel drains - remove top alternator mount bolts - Remove oil filter housing bolts but leave oil filter housing - remove grounding wire - remove fuel line zip ties - remove alternator fan shroud - lift engine - leave rigging in engine Currently we are transferring engine to the jig. | 10mm Socket, 3/8" impact gun, 19mm Ratcheting wrench, Phillips screw driver
Disassembly | 6 | Remove Fuel tank and Flip and Prep Chassis | 73 | 3 | 30 | [step 1] Install external fuel tank fittings [step 2] -Transfer Alternator mounts to new chassis - Transfer Engine mounts to new chassis - critical loosten motor mount screws when loaded this will help remove - load up fuel tank - remove perimeter fuel tank bolts - remove shipping blocks - lift chassis from containment tank - remove perimeter strap nuts - loosen top strap nuts - lift fuel tank to prevent fuel from leaking. - remove fuel tank hose - rotate barb on tank 180 degrees - Add 11ft of hose 3/8” fuel hose - rotate fuel tank inside of containment tank - install new fuel line ensuring not to get pinched - reinstall tank straps - bring chassis back over - drop chassis onto new fuel tank - reinstall perimeter bolts using crane to adjust your location [step 3] Install end mesh cover | 1” Socket, 11/16” socket, 3/8" impact gun, 19mm socket, 3/8” impact gun, 24mm socket, 14mm socket, 3/8” x 18” extension, 3/8" Angled electric impact, 13mm Socket, Long Phillips screw driver
Sub Assemblies | 7 | Battery Build | 0 | 1 | 0 | (no source steps) | 1 1/8” socket
Sub Assemblies | 8 | Panel rework station | 172 | 7 | 64 | [step 1] - Panel 4 - remove accessories - Remove hinges - remove louver box - remove accessories plate - remove bump stop - move panel to service parts bin - get updated panel 4 - reinstall bump stops - reinstall accessories plate - reinstall hinges - install foam on bottom edge of louver - install 1466 foam to top panel - install 1467 foam to bottom panel [step 2] - Panel 10 - remove baffle box - remove door handle - remove door hinges - reinstall door handles - reinstall hinges - Install baffle foam - install baffle box - drill out baffle screw hole if not aligned with step bit - if missing weldstud please disregard - install blocker plate with two nuts and two self tappers - install foam 1646 can possible be installed first. - Install 1469 - install 1470 - install 1468 - install perimeter gasket - start from bottom perimeter, work your way around the door. [step 3] - Panel 11 - remove baffle box - remove hinges - get new panel - install hinges - Install baffle foam first - Install lower baffle foam - install baffle - drill out holes if we need to - install side plate - install baffle nuts - install handle - install foam 1457 - install foam 1458 - install foam 1459 - install perimeter gasket [step 4] - Panel 9 - remove hinges - remove baffle box - if baffle box has foam on edges remove with scraper - remove handle ensure gasket comes of with handles - get new door - install door hinges - install handle - Install foam 1645 - install lower baffle seal- and press in place - install baffle box - drill holes if necessary - install side plate - install baffle box nuts - install side plate self tappers - may need to drill through rivets. That is okay here - install foam 1457 - install foam 1458 - install foam 1459 - install perimeter gasket [step 5] - Panel 3 - remove hinges interior door - remove hinges exterior - remove bumpers - get new panel - Install interior hinges - install exterior hinges - install foam 1456 - install foam 1477 - install perimeter foam seal on inside door [step 6] - Panel 6 - install edge foam gasket on outer edge of bolts - Install side foam inside of rivet hole - install radiator cover plate but leave access to fill - install foam 1463 first x2 - install foam 1475 - install foam 1476 [step 7] - Panel 5 - part of cooling stack - install 1460 - install 1461 - install 1462 - Install 1464 - install 1465 - install 1473 - install 1474 - install 1472 -Install 1471 | 10mm Socket, 13mm Socket, Phillips screw driver, 3/8” impact gun
Sub Assemblies | 9 | V2 Cooling system with Panel | 140 | 2 | 56 | [step 1] - Foam on V2 Cooling assembly - grab part 1300 - install foam 1478 - install foam 1479 - install foam 1480 [step 2] - Start with part 1300 with foam panels - add foam seal to bottom - punch some holes on the foam seal to allow bolt to go through - install part 1300 onto panel 5 - Install fans part 31 onto part 1300 - use part number 5 - chase threads if needed - install reservoir part 27 with part 3 - install foam gasket onto panel 3 - part 35 - Install radiator part 19 onto panel 3 - current radiator will need to have all holes widened with step bit - ensure the two radiator bolts are on top. - use part 3 with 7/16” washers to install radiator. - install foam tape on panel 3 for air duct. - install foam seal on radiator - Amended , bring part 1300 onto panel 3 - part 1300 will need the holes reemed out - Install with M6 x 30 with 7/16” washer - chase all threads on part 1300 - install cooling tower to panel 3 using part 3 with nuts and 7/16” washer - install inverter part 33 to part 32 using m6 x15mm - install inverter component on cooling tower with M6 x 30mm - will sit proud on bracket - install radiator plug part 21 3/4” hex socket - install drain system part, 22, 20, 16, 17 - Teflon between 16/17d - install part 28 and 20 onto radiator, orientation is important - remove radiator stop - install part 24,23,25,26 - install radiator hose with two hose clamps part 13 with part 18 - install inverter coolant hose adapter - install inverter 3/4” hose part 15 - use part 30 worm clamps - install f - move complete assembly to panel 5 - if needed keep the top bolts loose for the air inlet and radiator body bolts | 10mm Socket, 3/8” angled electric ratchet
Sub Assemblies | 10 | mVEC/DC2DC Build | 40 | 2 | 2 | [step 1] Mount mVec Relay box to Bracket. Mount DC 2 DC converter to bracket [step 2] Add wiring harness to assembly
Sub Assemblies | 11 | Upgrade Control Cabinet | 153 | 6 | 21 | [step 1] Install Din Rail with 2x Self Tappers. Mount tinkerer and the lock in place with Din Locks [step 2] Install 480v contactor, Install Can-bus junction. [step 3] Install wire harness for Tinkerer, Install resistor between A & B, Install Harness points to Can-Bus [step 4] Install MVEC 12v and can harness 1604 Route to front of control cabinet Connect can us connector Install ground Install control switch pin Install pin 3 [step 5] Install DC to Dc 12v harness and route to front of control cabinet Install canbus connector Install control switch [step 6] Move to final assembly Install Flexboost main harness Possibly install on cooling system first. Fan connectors Inverter connector Pump connectors E motor connector Clutch and resistor Install main harness ground with engine ground On control cabinet side Install Can 1 port. Install 480v 12v signal
Sub Assemblies | 12 | Build E Motor Assembly | 45 | 1 | 0 | Install motor coolant fittings Elbow fitting installed first. Then install Straight fitting | 26mm socket, 1/2” Ratchet, Crescent wrench, 1” socket
Sub Assemblies | 13 | Build Clutch Assembly with Housing | 145 | 9 | 50 | [step 1] Merge part 28 and 38 Align clutch cables and two holes so the cable comes out of the port Use part 10 as the hardware Torque to 47ftLbs [step 2] Split part 35 apart, only because of current containment action on loose bolt Use a flat head to separate Apply Mobilegrease XHP to Part 35 Shaft Wipe off area around the base of the shaft on part 35 and also the clutch side on part 38 108ftLbs of torque on hex bolt part 24 Install a small shim between part 39 and part 35 Install temporary clutch lock bolts to hold the clutch in place to prevent spinning 7/16”-20 bolts for clutch lock Critical - Remove Clutch lock bolts [step 3] Add pin to clutch pack bolt to prevent blackout. Containment action step. Ensure drill speed is set to 2200 First drill pass is with a mill bit Second drill part is with a drill bit. On second pass you are drilling though the shaft Install 3/16” x 1” tension pin into drilled hole area [step 4] Install clutch pin drive plate onto Diesel engine part 35 54ftlbs on all bolts Torque in a star pattern [step 5] Install clutch assembly Part 6 for the bolt to engine side using locking washers Install part 27 on top two bolts Torque bolts in star pattern to 54ftibs [step 6] Install part 16 with bolts part 24 onto clutch assembly Use 3/8” hex socket Torque to 108ftibs [step 7] Potential sub assembly - e motor with plates Remove E motor from crate with shackle kit Use part 13 bolts to attach part 41 to Emotor part 14. Keep note of the clocking direction. Top two bolts areas should match Torque to 54ftibs star pattern Install part 40 as well to back of E motor with part 3 with bolts Torque to 54IBSft start pattern [step 8] Install insert with grease Install shaft into e motor Install snap rings Lift e motor into diesel engine [step 9] Slide alternator to e motor | 9/16” socket, 3/8” impact gun, 3/8” torque wrench, Over head crane, Small shackle, Choker, Flathead screw driver, 3/8” hex socket, Angled electric ratchet, 1/2” torque wrench, Drill press, 11/16” ratcheting wrench, Cutting oil, Compressor, Punch set, 17mm socket, 3/8” electric angled ratchet, 3/8” Torque wrench, 3/8” angled electric ratchet, Pry bar, Torque wrench, Shackles, 8mm hex socket
Sub Assemblies | 14 | Upgrade engine / Alternator Assembly | 46 | 7 | 17 | [step 1] Alternator stack - Part 28 to part 31 - 30ftibs - 8 bolts [step 2] Part 17 - press on part 18 using press, Will need to use mallet to get part 18 passed the edge - add part 20 snap ring. Flip Part 17 over and add part 37 snap ring. [step 3] Chase threads out with tap and die [step 4] Install Insert 36 with mobilgrease xhp [step 5] Install flywheel adapter with m10x1.5x40mm on to the Alternator side Get all bolts started first before tightening down. Use new hardware only and the existing lock washers [step 6] Install part 28 onto alternator- Use crane to lift pilot bearing and support the alternator bearing. Start two bolts to get Part 28 Seated . Then install remaining bolts to 54FTIbs [step 7] Toque the Alternator Flywheel Adaptor to 54Ibs-ft Support the Rotor with a leverage bar while torquing. Mark each bolt with a wax pen | 6mm hex socket, 3/8” electric ratchet, Press, Snap ring pliers, M10 -1.5 tap and die, Air compressor, 17mm socket, 3/8” Electric Ratchet, 17mm Ratcheting wrench, 3/8" Electric Ratchet, Standard Ratchet, Crane, 3/8" Torque Wrench, Wax Marker, Offset Extension Wrench 3/8"
Sub Assemblies | 15 | Trailer Build | 240 | 0 | 0 | (no source steps)
Final Assembly | 16 | Merge Battery and chassis | 14 | 1 | 6 | - Connect chassis to crane - Ensure Battery wires are not in the way - lower chassis on to battery pack - Lower unit until you can use drift pin to set point - install 3/4 - 10 x 2” long bolts 12 total - ensure nut side is facing up - use Ear muffs when tightening - remove rigging straps | Crane, 1 1/8” socket, 1/2” Impact gun, 1 1/8” wrench
Final Assembly | 17 | Install Upgraded Powertrain Module | 25 | 1 | 12 | - Rig up engine and alternator assembly - Remove the alternator and engine mount bolts - move engine over and line up engine mounts and lower - then line up alternator mounts - install all mount nuts - install lower intercooler hose bolts - install oil filter housing - install oil drain - zip tie oil lines to chassis bar - install fuel selector on chassis - reinstall fuel lines supply and return - install barb with 7/8” socket and teflon | 19mm Ratcheting wrench
Final Assembly | 18 | Reinstall control cabinet | 81 | 6 | 32 | [step 1] - Install perimeter control cabinet bolts - install ground wire - reuse hardware [step 2] Install mVec sub assembly component self tappers - Install two self tapper on Mvec assembly - predrill with 1/8” drill bit - install two self tappers [step 3] - Install two self tapper on Mvec assembly - predrill with 1/8” drill bit - install two self tappers [step 4] - remove 24mm bolts and install wire bar. [step 5] - Unwrap wiring harness and begins reconnecting. - install ground on intake side. - install starter solenoid wire - zip tie wire harness to help with strain - install cabinet and main batter leads on starter - install insulation boot - install fuel sender wire - install containment overflow connector - finish zip tie to wire bar. - Install control cabinet harness main. - move to other side - start on end harness - install def harness connectors - install air pump connector -install exhaust valve connector - install charge air temp sensor - install mass air flow sensor - install inlet air temp sensor - install electric fuel pump connector - install EGR valve connector - install alternator connector - install alternator power connector - install crankcase pressure sensor - zip tie harness. [step 6] Install alternator wires They are all labeled and should be matched accordingly Connect the AVR | 8mm Socket, 24mm socket, 13mm Socket, 3/8" Electric Ratchet, 13mm wrench, 14mm socket, Flush cutters, Phillips screw driver
Final Assembly | 19 | Install Telematics | 15 | 1 | 0 | Pull wire down into the control cabinet. Connect LTE 1 to Antenna 1 Connect LTE 2 to Antenna 2 Connect GPS 1 to Antenna 4
Final Assembly | 20 | Install original cooling and after treatment system | 61 | 9 | 34 | [step 1] Install cooling assembly with crane. Lift and set in place [step 2] - Align cooling assembly with chassis - aligned Def tank - install 4 front screws - install all perimeter cooling assembly bolts - use mallet if needed to get bolts to line up - reuse hardware from Disassembly. [step 3] - Install Def tank - use M8 x 1.25 x 25mm [step 4] - Install Def Cover - 14x 10mm bolts - 2x bolts underneath. [step 5] - Install lower intercooler hose - tighten crossover pipe bolts - install upper intercooler hose [step 6] - Install upper radiator hose - install lower radiator hose - install front side def hose 03022 - install back side def hose 03018 - install zip tie on lower radiator hose and trim - install coolant drain [step 7] - Install Fan Shroud - install one corner bolt - then install opposite side corner bolt - then install remaining bolts 13x [step 8] - Install Exhaust - install exhaust valve with gaskets - install 4x exhaust bolts from front to back - install valve air line [step 9]
Final Assembly | 21 | Install V2 Cooling system | 15 | 1 | 0 | Install pump install hoses Hose from Pump to 90 degree e motor = 24" hose from pump to HE Drain = 14" Hose from Inverter to E Motor straight kit = 26.25"
Final Assembly | 22 | Reinstall the panel system | 179 | 18 | 44 | [step 1] Install airmen panel 1 Install M8 bolts loosely Reuse hardware [step 2] Install Airment panel 2 [step 3] Install cross bar on def side [step 4] Install panel 6 Use 3 eye hooks on panel with strapping There are alignment pins located on by the diesel engine and the sides. Ensure those are aligned. Install bolts loosely. [step 5] Install Cross member Pick cross member with crane Loosen top crossmember bolts with 24mm Install chassis bolts for crossmember loosely [step 6] Install Panel 4 Install bolts loosely [step 7] Install Panel 3-5 or V2 Cooling assembly systems [step 8] Install fuel line bracket [step 9] Install oil filter bracket - add to cross member before installing cross member. [step 10] Install Airmen panel cross member by controls Install loosely [step 11] Tighten all installed panel hardware. Make panels flush on the outside and tighten Tighten cross member bolts Tighten oil filter housing bracket [step 12] Install exhaust hanger extension bracket [step 13] Install air cleaner assembly Re use hard ware. [step 14] Install airmen DEF side end panels [step 15] Install CAB side Airmen end panels Connect E Stop. [step 16] Install doors [step 17] Install cover grommets [step 18] Install top door trim panel Install grommet Install bottom door trim panel | 24mm socket, 13mm Socket, 3/8" Angled electric impact, 3/8" impact gun, 24mm wrench, 13mm wrench
Final Assembly | 23 | Fluid Replenishment | 30 | 0 | 0 | (no source steps)
Final Assembly | 24 | Install on trailer | 30 | 1 | 0 | (no source steps)